## Order Log
Production order tracking log
Yellow cells with blue text are for you to fill in. White cells calculate automatically. Row 7 is an example, so overwrite it. Free template from Apparel Search (apparelsearch.com).
Brand and season | Your Brand, Spring 2027
|  |  |  | Planned dates |  |  |  |  | Actual dates
PO number | Style or description | Factory | Units | PO date | Fabric in | Production start | Ex-factory | Delivery to you | Fabric in | Ex-factory | Delivery to you | Days late | Status | Auto flag | Next action or notes
PO-4521 | Women's woven shirt, 3 colors | Factory A | 1000 | 2026-12-01 | 2027-01-10 | 2027-01-25 | 2027-03-01 | 2027-04-15 |  |  |  | 0 | On track |  | Awaiting fabric
Summary
Orders logged |  |  | 1
Total units |  |  | 1000
Delivered |  |  | 0
Past planned delivery, not yet delivered |  |  | 0
Delivered late |  |  | 0
Average days late on delivered orders
Days late compares your actual delivery with the planned delivery, or today while the order has not arrived. The Status column is your own judgment. The Auto flag is calculated from the dates. Rows turn red when past the planned delivery date, amber when delivered late and green when delivered on time.
Free templates from Apparel Search. More at www.ApparelSearch.com/downloadable-templates/downloadable_templates_fashion_industry.html
Formulas:
Days late = IF([Delivery to you]="","",IF([Delivery to you]<>"",MAX(0,[Delivery to you]-[Delivery to you]),MAX(0,TODAY()-[Delivery to you])))
Auto flag = IF([PO number]="","",IF([Delivery to you]<>"",IF([Delivery to you]>[Delivery to you],"Delivered late","Delivered"),IF(AND([Delivery to you]<>"",TODAY()>[Delivery to you]),"Past planned delivery","")))