## T&A Calendar
Time and action (T&A) calendar |  |  | Free template from Apparel Search (ApparelSearch.com). More free templates: apparelsearch.com/downloadable-templates
Yellow cells with blue text are for you to fill in. White cells calculate automatically. Row 1 of each table is an example, so overwrite it. Free template from Apparel Search (apparelsearch.com). To skip a step, set its days to 0.
| Style or PO | Fall woven shirts
| Target delivery date (goods in your warehouse) | 2027-12-01
| Production type (for your reference) | Overseas
# | Milestone | Owner | Days | Counts as | Start date | Due date | Status | Actual date | Notes
1 | Design and tech pack | Brand | 14 | Calendar | 2027-06-05 | 2027-06-19 | Not started |  | Example owner and note, overwrite
2 | Sampling and approvals |  | 35 | Calendar | 2027-06-19 | 2027-07-24 | Not started
3 | Fabric and trim sourcing |  | 30 | Calendar | 2027-07-24 | 2027-08-23 | Not started
4 | Production |  | 35 | Calendar | 2027-08-23 | 2027-09-27 | Not started
5 | Quality inspection | Factory | 5 | Working | 2027-09-27 | 2027-10-04 | Not started
6 | Factory to port and export documents |  | 5 | Working | 2027-10-04 | 2027-10-09 | Not started
7 | Ocean or air transit |  | 30 | Calendar | 2027-10-09 | 2027-11-08 | Not started
8 | Port arrival and offloading |  | 4 | Working | 2027-11-08 | 2027-11-12 | Not started
9 | Customs clearance |  | 3 | Working | 2027-11-12 | 2027-11-17 | Not started
10 | Delivery to your warehouse |  | 4 | Calendar | 2027-11-17 | 2027-11-21 | Not started
11 | Buffer for delays |  | 10 | Calendar | 2027-11-21 | 2027-12-01 | Not started
12 | Spare step (name it and set days) |  | 0 | Calendar | 2027-12-01 | 2027-12-01 | Not started
13 | Spare step (name it and set days) |  | 0 | Calendar | 2027-12-01 | 2027-12-01 | Not started
14 | Spare step (name it and set days) |  | 0 | Calendar | 2027-12-01 | 2027-12-01 | Not started
| Latest start date | 2027-06-05
| Total span (calendar days) | 179
| Today (updates automatically) | 2026-10-20
The calendar works backward from your target delivery date: each step ends where the next one starts. Steps marked Calendar count every day. Steps marked Working skip weekends only. Public holidays and factory closures are not included, so allow extra time. Durations are placeholders, so replace them with lead times from your own suppliers.
Rows turn red when a step is past due and not marked Done, and green when Done.
Formulas:
Start date = IF([Counts as]="Working",WORKDAY([Due date],-[Days]),[Due date]-[Days])
Due date = [Start date, row below]